## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-01 | Project environment Setup (JDK, SPRING,MYSQL DB,Intellij IDE) | MUST HAVE | US-01 | Shweta Suryawanshi | 3- Completed
S1 | S1 | US-02 | Creating SpringBoot Application with thier Dependancy like Spring Web,MYSQL Driver & Thyemleaf | MUST HAVE | US-02 | Shweta Suryawanshi | 3- Completed
S1 | S1 | US-03 | Implemented Task CRUD operation using Thyemleaf UI | MUST HAVE | US-03 | Shweta Suryawanshi | 3- Completed
S1 | S1 | US-04 | Added Features like sorting,filtering & Pagination UI | MUST HAVE | US-04 | Shweta Suryawanshi | 3- Completed
S2 | S2 | US-05 | Add Enums (status,Priority) with UI improvements | MUST HAVE | US-05 | Shweta Suryawanshi | 3- Completed
S2 | S2 | US-06 | Implement REST APIs for Task CRUD Operations | MUST HAVE | US-06 | Shweta Suryawanshi | 3- Completed
S2 | S2 | US-07 | Add REST APIs for filtering , sorting & Pagination | MUST HAVE | US-07 | Shweta Suryawanshi | 3- Completed
S3 | S3 | US-08 | API testing via Postman with final cleanup | MUST HAVE | US-08 | Shweta Suryawanshi | 3- Completed
S3 | S3 | US-09 | Implementing JUNIT , Mockito for tesing APIs | MUST HAVE | US-09 | Shweta Suryawanshi | 3- Completed
S3 | S3 | US-10 | creating User Authentication feature to Application | MUST HAVE | US-10 | Shweta Suryawanshi | 3- Completed
S4 | S4 | US-11 | Implementeing User Registeration and login logics with api | MUST HAVE | US-11 | Shweta Suryawanshi | 3- Completed
S4 | S4 | US-12 | Adding feature like user can receive OTP verification Email to there registered email | MUST HAVE | US-12 | Shweta Suryawanshi | 3- Completed
S4 | S4 | US-13 | Adding HTTPSession that user can register/login after verification within 5 minutes | MUST HAVE | US-13 | Shweta Suryawanshi | 3- Completed
Note on F1: ====== ID#AAAByJt0yTE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 78 | 38 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-1 | Install JDK, IntelliJ IDEA and MySQL | 2025-11-27 | 2025-11-28 | Shweta | Installation | 3-Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-2 | Configure Spring Boot project & application.properties | 2025-11-28 | 2025-11-29 | Shweta | Configuration | 3-Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-1 | Create Spring Boot project with Spring Web & Thymeleaf | 2025-11-29 | 2025-11-30 | Shweta | others | 3-Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-2 | Add MySQL Driver & configure database connection | 2025-11-30 | 2025-12-01 | Shweta | Coding | 3-Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-1 | Design Task entity, repository & service layer | 2025-12-01 | 2025-12-02 | Shweta | Coding | 3-Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-2 | Create Thymeleaf pages for Create, Update, Delete & View Task | 2025-12-02 | 2025-12-03 | Shweta | Coding | 3-Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-1 | Implement sorting & filtering logic in backend | 2025-12-03 | 2025-12-04 | Shweta | Coding | 3-Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-2 | Integrate pagination, sorting & filtering in Thymeleaf UI | 2025-12-04 | 2025-12-05 | Shweta | Coding | 3-Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-1 | Create enums for Task Status and Priority | 2025-12-05 | 2025-12-06 | Shweta | Coding | 3-Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-2 | Bind enums with UI dropdowns and improve UI display | 2025-12-06 | 2025-12-07 | Shweta | Coding | 3-Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-1 | Develop REST APIs for Create & Update Task | 2025-12-07 | 2025-12-08 | Shweta | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-2 | Develop REST APIs for Read & Delete Task | 2025-12-08 | 2025-12-09 | Shweta | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-1 | Create REST APIs for filtering and sorting tasks | 2025-12-09 | 2025-12-10 | Shweta | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-2 | Implement pagination support in REST APIs | 2025-12-10 | 2025-12-11 | Shweta | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-1 | Test Task CRUD APIs using Postman | 2025-12-11 | 2025-12-12 | Shweta | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-2 | Validate sorting, filtering & pagination APIs | 2025-12-12 | 2025-12-13 | Shweta | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-9 | T-1 | Write unit tests for service layer using Junit | 2025-12-13 | 2025-12-14 | Shweta | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-9 | T-2 | Mock repository layer using Mockito | 2025-12-14 | 2025-12-15 | Shweta | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-1 | Implement User entity, repository & service | 2025-12-15 | 2025-12-16 | Shweta | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-2 | Create login functionality with validation user registration REST API | 2025-12-16 | 2025-12-17 | Shweta | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-1 | Develop login REST API with authentication logic | 2025-12-17 | 2025-12-18 | Shweta | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-2 | Implement OTP generation & email sending Verify OTP and activate user account | 2025-12-18 | 2025-12-19 | Shweta | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-1 | Creating User Dashboard with task analytics | 2025-12-19 | 2025-12-20 | Shweta | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-2 | Improving UI | 2025-12-20 | 2025-12-21 | Shweta | Coding | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAAByJt0yTg Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAAByJt0yTo Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAAByJt0yT4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAAByJt0yTQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAAByJt0yTk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAAByJt0yTM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAAByJt0yTA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAAByJt0yTY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAAByJt0yT0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAAByJt0yTU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAAByJt0yTI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAAByJt0yTc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAAByJt0yTs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAAByJt0yTw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAAByJt0yT8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAAByJt0yS4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAAByJt0yS8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Issue in configuring MySQL database connection | Reviewed application.properties and fixed database configuration
Sprint 1 | Day 3 | Confusion in project folder structure | Followed standard Spring Boot package structure and refactored code
Sprint 2 | Day 5 | Difficulty in implementing Thymeleaf CRUD forms | Referred official Thymeleaf documentation and corrected form binding
Sprint 2 | Day 6 | Pagination and sorting not working properly in UI | Fixed controller logic and verified request parameters
Sprint 2 | Day 7 | Form validation not working | Fixed validation and error messages
Sprint 3 | Day 9 | REST API returning incorrect response format | Updated DTOs and added proper response mapping
Sprint 3 | Day 12 | Errors while writing unit tests using Mockito | Corrected mock setup and added proper annotations
Sprint 4 | Day 16 | OTP email not delivered consistently | Verified SMTP configuration and regenerated app password

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 27/11/2025 | 2025-10-12 | Shweta Suryawanshi | Verifying environment and dependencies before coding | Starting work without setup chec | Following Spring Boot project structure | Completed project setup and configuration
2 | Sprint 2 | 2025-11-12 | 24/12/2025 | Shweta Suryawanshi | UI planning using Thymeleaf and Bootstrap | Hardcoding values in UI | Implementing CRUD step-by-step | Completed Task CRUD with UI
3 | Sprint 3 | 26/12/2025 | 2026-09-01 | Shweta Suryawanshi | Writing REST APIs with proper standard | Manual testing only | Using Postman and JUnit for testing | Completed REST APIs and testing
4 | Sprint 4 | 2025-12-01 | 21/1/2025 | Shweta Suryawanshi | Implementing security using OTP verification | Allowing login without verification | Input validation and session handling | Completed authentication with OTP & session expiry
5
6
7